## Sheet1
Phase II estimation
Legend:
Numerical representation of a day: | 1
2 hours of work: | 0.25
4 hours of work: | 0.5
6 hours of work: | 0.75
8 hours of work (full day): | 1
Please note that the estimation will include the customization of the modules if needed and daily support of the application
Module | Item | Needs clarification / meeting | Fastest estimation | Lowest estimation
MyReport | Tested mockups | No | 0.5 | 1
| Filter engine | Most likely | 1 | 3
| Graphical representation of filters | No | 0.25 | 0.25
| Chart and diagram engine | No | 4 | 5
| Graphical representation of charts / diagrams | Yes | 3 | 4
| Building an interface | No | 1 | 1
| Styling | Most likely | 0.25 | 1
| Testing | No | 1 | 2
Fault book | Photo attachment | No | 1 | 1
| Action to be taken interface | Yes | 2 | 3
| Mockups | Yes | 2 | 3
| Test | No | 1 | 1
| Development | No | 3 | 4
| Implementation | No | 0.5 | 1
| Testing | No | 1 | 2
UserTrackingSystem | Google Analytics
| Setup | No | 0.25 | 0.25
| Report Customization | Most likely | 2 | 3
| Report Scheduling | Yes | 0.25 | 0.25
Local precise authentication reporting
| Setup | No | 1 | 2
| Report Customization | Most likely | 2 | 3
| Report Scheduling | Yes | 0.25 | 0.25
Custom User UX* tracking system
| Setup | No | 0.5 | 1
| Report Customization | Most likely | 2.5 | 4.5
| Report Scheduling | Yes | 0.25 | 0.25
Search Engine | Mockups | Yes | 2 | 3
| Test | No | 0.5 | 0.75
| Build | No | 4 | 7
| Implement | No | 1 | 1
| Test | No | 2 | 3
Feedback system | Form | Yes | 0.75 | 1.5
| Scheduling | Yes | 0.25 | 0.75
Investigation | Purchase | Yes | 3 | 4
| Initialization | Yes | 5 | 10
| Testing | Yes | 5 | 10
Excel data input | Implementation | No | 0.5 | 0.5
| Template creation for further use | No | 0.5 | 0.5
Total: |  |  | 55 | 88.75